## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US1 | As a developer, I want to collect visa processing dataset so that I can train the model. | MUST HAVE | Dataset Availability | Gouransh | 3- Completed
Sprint 1 | Sprint 1 | US2 | I want to collect visa processing dataset so that I can train the model. | MUST HAVE | US1 | Gouransh | 3- Completed
Sprint 1 | Sprint 1 | US3 | I want to clean the dataset to remove missing and invalid values. | MUST HAVE | US2 | Gouransh | 3- Completed
Sprint 2 | Sprint 2 | US4 | I want to perform EDA to understand the dataset. | MUST HAVE | US3 | Gouransh | 3- Completed
Sprint 2 | Sprint 2 | US5 | I want to visualize trends using charts. | SHOULD HAVE | US4 | Gouransh | 3- Completed
Sprint 2 | Sprint 2 | US6 | I want to create features like risk score and seasonal index. | MUST HAVE | US4 | Gouransh | 3- Completed
Sprint 3 | Sprint 3 | US7 | I want to train machine learning models for prediction | MUST HAVE | US6 | Gouransh | 3- Completed
Sprint 3 | Sprint 3 | US8 | I want to train machine learning models for prediction | MUST HAVE | US7 | Gouransh | 3- Completed
Sprint 3 | Sprint 3 | US9 | I want to select the best model for deployment | MUST HAVE | US8 | Gouransh | 3- Completed
Sprint 4 | Sprint 4 | US10 | As a user, I want to enter visa details in a form. | MUST HAVE | None | Gouransh | 3- Completed
Sprint 4 | Sprint 4 | US11 | As a user, I want to get visa processing time prediction. | MUST HAVE | US9 | Gouransh | 3- Completed
Sprint 4 | Sprint 4 | US12 | As a developer, I want to build backend using Flask API. | MUST HAVE | US9 | Gouransh | 3- Completed
Sprint 4 | Sprint 4 | US13 | As a developer, I want to connect frontend with backend. | MUST HAVE | US12 | Gouransh | 3- Completed
Sprint 4 | Sprint 4 | US14 | As a user, I want to select target country from dropdown. | MUST HAVE | US10 | Gouransh | 3- Completed
Sprint 4 | Sprint 4 | US15 | As a user, I want responsive UI for better experience. | SHOULD HAVE | US10 | Gouransh | 3- Completed
Sprint 4 | Sprint 4 | US16 | As a user, I want to see charts and visualizations. | COULD HAVE | US11 | Gouransh | 3- Completed
Sprint 4 | Sprint 4 | US17 | As a developer, I want to deploy app on Render. | MUST HAVE | US13 | Gouransh | 3- Completed
Sprint 4 | Sprint 4 | US18 | As a developer, I want to test the application. | MUST HAVE | US17 | Gouransh | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US1 | T1 | Collect Visa Dataset | 2026-01-01 | 2026-01-02 | Gouransh | Data Collection | Completed | 4
US2 | T2 | Data Cleaning (remove null values) | 2026-01-03 | 2026-01-05 | Gouransh | Data Preprocessing | Completed | 6
US3 | T3 | Data preprocessing & formatting | 2026-01-06 | 2026-01-08 | Gouransh | Data Preprocessing | Completed | 6
US4 | T4 | Perform EDA analysis | 2026-01-09 | 2026-01-11 | Gouransh | Analysis | Completed | 6
US5 | T5 | Create visualizations (charts) | 2026-01-12 | 2026-01-14 | Gouransh | Visualization | Completed | 6
US6 | T6 | Feature engineering (risk score, seasonal index) | 2026-01-15 | 2026-01-18 | Gouransh | Feature Engineering | Completed | 8
US7 | T7 | Train ML Model | 2026-01-19 | 2026-01-23 | Gouransh | Model Training | Completed | 8
US8 | T8 | Model evaluation and comparison | 2026-01-24 | 2026-01-26 | Gouransh | Evaluation | Completed | 6
US9 | T9 | Select best model (Linear Regression) | 2026-01-27 | 2026-01-28 | Gouransh | Evaluation | Completed | 4
US10 | T10 | Design Frontend UI | 2026-01-29 | 2026-02-02 | Gouransh | UI Development | Completed | 8
US11 | T11 | Implement Flask backend API | 2026-02-03 | 2026-02-05 | Gouransh | Backend Development | Completed | 6
US12 | T12 | Integrate frontend + backend | 2026-02-06 | 2026-02-08 | Gouransh | Integration | Completed | 6
US13 | T13 | Deploy on Render and Testing | 2026-02-09 | 2026-02-10 | Gouransh | Deployment | Completed | 4

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Dataset had missing values and inconsistent formats | Performed data cleaning and handled missing values using preprocessing techniques
Sprint 1 | Day 4 | Difficulty understanding dataset features | Performed data exploration and analyzed feature distributions
Sprint 2 | Day 6 | Selecting important features for model | Used correlation analysis and visualization techniques
Sprint 2 | Day 8 | Difficulty creating meaningful features | Created derived features like risk_score and seasonal_index
Sprint 3 | Day 10 | Model training took too much time (Random Forest) | Reduced hyperparameters and used smaller grid search
Sprint 3 | Day 11 | Confusion in selecting best model | Compared model using MAE, RMSE, and R2 score
Sprint 4 | Day 12 | Difficulty in connecting frontend with backend | Used Flask API and JSON request handling
Sprint 4 | Day 13 | Deployment failed due to python version issue | Changed python version to 3.10 using runtime.txt
Sprint 4 | Day 14 | Scikit-learn installation error during deployment | Fixed dependency issues and ensured compatible versions

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-01-01 | 2026-01-08 | Gouransh Pathak | Start proper data cleaning and preprocessing techniques | Stop using raw dataset without cleaning | Continue analyzing dataset features | Cleaned dataset and handled missing values
2 | Sprint 2 | 2026-01-09 | 2026-01-18 | Gouransh Pathak | Start using visualization for data analytics | Stop selecting features randomly | Continue Feature Engineering | Created new features like risk score and seasonal_index
3 | Sprint 3 | 2026-01-19 | 2026-01-28 | Gouransh Pathak | Start comparing multiple ML models | Stop relying on a single model | Continue model evaluation | Compared Linear Regression and Random Forest
4 | Sprint 4 | 2026-01-29 | 2026-02-03 | Gouransh Pathak | Start hyperparameter tuning | Stop using default model parameters | Continue performance comparison | Tuned Random Forest model
5 | Sprint 4 | 2026-02-04 | 2026-02-07 | Gouransh Pathak | Start building frontend UI | Stop focusing only on backend | Continue integrating ML model | Developed responsive UI using HTML, CSS, JS
6 | Sprint 4 | 2026-02-08 | 2026-02-09 | Gouransh Pathak | Start connecting frontend with backend | Stop manual testing | Continue API testing | Connected Flask API with frontend
7 | Sprint 4 | 2026-02-09 | 2026-02-10 | Gouransh Pathak | Start deploying application | Stop running only local environment | Continue debugging | Deployed project on Render and fixed Python version issues