## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Gouransh Pathak | 2026-02-05 | Prediction not showing after form submission | Sprint 4 | Gouransh Pathak | Logical | Fixed API connection between frontend and Flask backend | 2026-02-05 | Closed | Issue resolved after fixing fetch request
2 | Gouransh Pathak | 2026-02-06 | Description: UI not responsive on mobile devices | Sprint 4 | Gouransh Pathak | User Interface | Added responsive CSS using flexbox and media queries | 2026-02-06 | Closed | UI now works on all devices
3 | Gouransh Pathak | 2026-02-07 | Country dropdown not showing all countries | Sprint 4 | Gouransh Pathak | User Interface | Implemented searchable dropdown with all countries | 2026-02-07 | Closed | Improved user experience
4 | Gouransh Pathak | 2026-02-08 | Model giving incorrect predictions for some inputs | Sprint 4 | Gouransh Pathak | Logical | Improved feature engineering and retrained model | 2026-02-08 | Closed | Accuracy improved
5 | Gouransh Pathak | 2026-02-09 | Deployment failed due to Python version incompatibility | Sprint 4 | Gouransh Pathak | Standards | Set Python version to 3.10.13 in environment variables | 2026-02-09 | Closed | Deployment successful
6 | Gouransh Pathak | 2026-02-09 | scikit-learn installation error during deployment | Sprint 4 | Gouransh Pathak | Maintainability | Fixed requirements.txt and removed duplicate entries | 2026-02-09 | Closed | Build successful
7 | Gouransh Pathak | 2026-02-10 | Charts not rendering properly | Sprint 4 | Gouransh Pathak | User Interface | Fixed chart library integration and data format | 2026-02-10 | Closed | Visualizations working properly